## Master Checklist
TUM MSc Robotics, Cognition & Intelligence — Application Checklist (Winter 2027)
# | Task / Document | Category | Deadline | Status | Notes
PHASE 1 — Start Immediately (June 2026)
1 | Apply for APS Certificate at German Embassy | India-Specific | June 2026 | ☐ Not Started | Takes 2–4 months; needed for uni-assist VPD
2 | Enroll in German language course (target B1/B2) | Language | Ongoing | ☐ Not Started | Program has German-taught modules
3 | Take GRE diagnostic test (free on ETS website) | GRE Prep | June 2026 | ☐ Not Started | Identify weak areas before full prep
4 | Collect all VIT transcripts (official copies) | Documents | June 2026 | ☐ Not Started | Get multiple certified copies
5 | Obtain VIT module handbook / course curriculum | Documents | June 2026 | ☐ Not Started | Required for Curricular Analysis form
PHASE 2 — Mid Preparation (July – September 2026)
6 | Complete GRE focused preparation | GRE Prep | Jul–Aug 2026 | ☐ Not Started | Target: Quant 164+, AW 4.0+
7 | Appear for GRE (first attempt) | GRE Prep | Sep 2026 | ☐ Not Started | Book slot at Chennai test center (~₹18,000)
8 | Start IELTS/TOEFL preparation | Language | Jul–Aug 2026 | ☐ Not Started | English proficiency proof required
9 | Appear for IELTS or TOEFL | Language | Sep 2026 | ☐ Not Started | Check TUM's accepted certificates list
10 | Begin German proficiency exam prep (TestDaF/Goethe) | Language | Ongoing | ☐ Not Started | Check TUM's required German level for RCI
PHASE 3 — Application Prep (October – December 2026)
11 | GRE retake if score below 164 Quant | GRE Prep | Nov 2026 | ☐ Not Started | Scores valid 5 years
12 | Appear for German language exam | Language | Oct–Nov 2026 | ☐ Not Started | Get official certificate
13 | Draft Motivation Letter (max 2 pages) | Application Docs | Nov 2026 | ☐ Not Started | Be specific to RCI program
14 | Write Academic Essay (~1000 words) | Application Docs | Nov 2026 | ☐ Not Started | Written independently; check TUM topic
15 | Prepare CV (tabular format) | Application Docs | Nov 2026 | ☐ Not Started | Academic + project + internship experience
16 | Fill Curricular Analysis Excel form | Application Docs | Dec 2026 | ☐ Not Started | Map VIT BTech courses to TUM requirements
17 | Register on uni-assist and start VPD process | India-Specific | Nov 2026 | ☐ Not Started | Needs APS certificate + transcripts
18 | Get APS Certificate (should arrive by now) | India-Specific | Nov 2026 | ☐ Not Started | Follow up with German embassy if delayed
19 | Get documents translated/notarized if required | Documents | Dec 2026 | ☐ Not Started | Check TUM requirements for Indian docs
20 | Collect passport-size photographs | Documents | Dec 2026 | ☐ Not Started | ID-style photo required
PHASE 4 — Submit Application (February – March 2027)
21 | Create TUMonline account | Application | Feb 1, 2027 | ☐ Not Started | Personal data cannot be edited after creation
22 | Fill online application on TUMonline | Application | Feb 2027 | ☐ Not Started | 11-step process
23 | Upload all documents on TUMonline | Application | Feb–Mar 2027 | ☐ Not Started | Cannot be exchanged after submission
24 | Submit uni-assist VPD | India-Specific | Feb–Mar 2027 | ☐ Not Started | Run parallel to TUM application
25 | Submit complete application (HARD DEADLINE) | Application | Mar 31, 2027 | ☐ Not Started | Visa applicants deadline — do NOT miss this
PHASE 5 — Post Application
26 | Track application status on TUMonline | Post-Application | Apr 2027 | ☐ Not Started | Do not enquire about individual doc status
27 | Prepare for admissions interview (Stage 2) | Post-Application | Apr–May 2027 | ☐ Not Started | 20–30 min interview if shortlisted
28 | Apply for German student visa immediately on offer | Visa | On admission | ☐ Not Started | Apply at German embassy/consulate in India
29 | Arrange German public health insurance | Enrollment | Before enroll | ☐ Not Started | Mandatory for TUM enrollment
30 | Pay tuition fee (€6,000/semester) | Enrollment | Before enroll | ☐ Not Started | Check scholarship/waiver options early

## Documents Checklist
TUM RCI — Documents Checklist
# | Document | Type | Status | Notes
Mandatory — All Applicants
1 | Bachelor's Degree Certificate | Academic | ☐ Not Ready | Final certificate after graduation
2 | Official Transcripts (all semesters) | Academic | ☐ Not Ready | Get multiple certified copies from VIT
3 | VIT Module Handbook / Course Syllabus | Academic | ☐ Not Ready | For curricular analysis mapping
4 | Curricular Analysis Form (Excel) | Application | ☐ Not Ready | Download template from TUM RCI page
5 | Motivation Letter (max 2 pages) | Application | ☐ Not Ready | Specific to RCI program
6 | Academic Essay (~1000 words) | Application | ☐ Not Ready | Independent writing on TUM-given topic
7 | CV (tabular format) | Application | ☐ Not Ready | Include projects, internships, research
8 | Passport (valid copy) | Identity | ☐ Not Ready | Ensure passport validity through 2028+
9 | Passport-size photograph (ID style) | Identity | ☐ Not Ready
Language Certificates
10 | English Proficiency (IELTS/TOEFL) | Language | ☐ Not Ready | Check TUM's accepted certificates list
11 | German Proficiency Certificate | Language | ☐ Not Ready | TestDaF / Goethe / DSH — check required level
India-Specific Documents
12 | APS Certificate | India-Specific | ☐ Not Ready | Apply at German embassy in India ASAP
13 | GRE Score Report | India-Specific | ☐ Not Ready | Min: Quant 164, AW 4.0 — send via ETS
14 | VPD from uni-assist | India-Specific | ☐ Not Ready | Preliminary Documentation for non-EU degrees
For Enrollment (After Admission)
15 | Signed Enrollment Application | Enrollment | ☐ Not Ready | After receiving offer letter
16 | Authenticated Degree + Transcripts | Enrollment | ☐ Not Ready | Original certified copies
17 | German Health Insurance Confirmation | Enrollment | ☐ Not Ready | Mandatory — TK, AOK, Barmer etc.
18 | German Student Visa | Visa | ☐ Not Ready | Apply at German embassy/consulate India

## Timeline
TUM RCI — Application Timeline (Winter 2027)
Period | Milestone | Status | Notes
Jun 2026 | Apply for APS Certificate | ☐ Pending | Longest wait — do this first
Jun 2026 | Enroll in German language class | ☐ Pending | Aim for B1 by Dec 2026, B2 by Mar 2027
Jun 2026 | GRE diagnostic test | ☐ Pending | Free on ETS website
Jun–Aug 2026 | GRE focused preparation | ☐ Pending | 4–6 weeks dedicated prep
Jul–Aug 2026 | IELTS/TOEFL preparation | ☐ Pending
Sep 2026 | GRE First Attempt | ☐ Pending | Target: Quant 164+, AW 4.0+
Sep 2026 | IELTS/TOEFL Exam | ☐ Pending
Oct–Nov 2026 | GRE Retake (if needed) | ☐ Pending
Oct–Nov 2026 | German language exam (TestDaF/Goethe) | ☐ Pending
Nov 2026 | APS Certificate should arrive | ☐ Pending | Follow up with embassy if delayed
Nov 2026 | Draft Motivation Letter + Essay + CV | ☐ Pending | Get reviewed by peers/mentors
Nov–Dec 2026 | Register on uni-assist, start VPD | ☐ Pending | Needs APS + transcripts
Dec 2026 | Complete Curricular Analysis form | ☐ Pending | Map VIT courses to TUM RCI
Dec 2026 | Finalize all documents | ☐ Pending | Nothing should be pending after this
Feb 1, 2027 | Application window OPENS | ☐ Pending | Create TUMonline account
Feb 2027 | Submit TUM online application | ☐ Pending | Upload all documents
Mar 31, 2027 | APPLICATION DEADLINE (visa applicants) — HARD | ☐ Pending | DO NOT MISS THIS
Apr–May 2027 | Wait for Stage 1 result | ☐ Pending | Track on TUMonline
May–Jun 2027 | Admissions Interview (Stage 2, if shortlisted) | ☐ Pending | 20–30 min with admissions committee
Jun–Jul 2027 | Receive admission decision | ☐ Pending
On Admission | Apply for German student visa immediately | ☐ Pending | German embassy/consulate India
Before Enroll | Arrange German health insurance | ☐ Pending | TK, AOK, Barmer etc.
Oct 2027 | Winter semester begins | ☐ Pending | You're in!

## GRE Quick Guide
GRE Quick Reference — TUM RCI Requirements
Section | Max Score | TUM Minimum | Tips
Quantitative Reasoning | 170 | 164 (required) | 10th–12th grade math — very doable for BTech CSE
Verbal Reasoning | 170 | No minimum set | Focus on reading comprehension; improve vocabulary
Analytical Writing | 6.0 | 4.0 (required) | Write 2 essays — practice argument analysis
Prep Resources
ETS Official GRE Website | Free | free diagnostic + official practice tests
Manhattan Prep 5 lb. Book | Paid | Best for Quant practice — 1000+ questions
Magoosh GRE | Paid | Good video explanations + adaptive practice
Gregmat (YouTube/website) | Free/Paid | Excellent for Verbal + essay strategy